## TFU 2nd qtr 2021
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2ND QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Bigasan Livelihood Project |  | Toboy & San Vicente West, Asingan, pangasinan | 999300 | 2021-05-31 | 2021-06-15 | 1.071% | 10700
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor

## TFU 1st qtr 2021 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
CONSTRUCTION OF DRAINAGE CANAL IN BRGY. MCALONG - DOMANPOT |  | MACALONG - DOMANPOT, ASINGAN, PANGASINAN | 3998766.72 | 2020-10-27 | 2021-02-04 | 100% | 3998766.72 |  | AM2020 | 0 | 0
CONSTRUCTION OF LINED CANAL & BOX CULVERT IN ZONE 1 OF BRGY. MACALONG |  | ZONE 1, BRGY. MACALONG, ASINGAN, PANGASINAN | 1622182.53 | 2020-10-27 | 2021-01-05 | 100% | 1622182.53 |  | AM2020 | 0 | 0
UPGRADING OF PUGONG ROAD IN BARANGAY ARISTON EAST |  | SITIO PUGONG, BRGY. ARISTON EAST, ASINGAN, PANGASINAN | 2998658.73 | 2020-10-27 | 2020-12-11 | 100% | 2998658.73 |  | AM2020 |  | 0
UPGRADING OF COLDIT - SAN VICENTE ROAD IN BRGY. COLDIT AND SAN VICENTE WEST |  | BRGY. COLDIT - SAN VICENTE WEST, ASINGAN, PANGASINAN | 2998931.85 | 2020-10-27 | 2020-12-11 | 100% | 2998931.85 |  | AM2020 |  | 0
Concreting of farm to market road at Carosucan Norte-Carosucan Sur, Asingan, Pangasinan |  | Carosucan Norte - Carosucan Sur, Asingan, Pangasinan | 946485 | 2020-12-04 | 2021-01-03 | 100% | 946485 |  | Excise Tax (LBM#79) | 0 | 0
Enclosure of Cottages for Isolation at Brgy. Macalong, Asingan, Pangasinan PO Date: 03/02/2021 SWA: 03/10/2021 |  | Macalong, Asingan, Pangasinan | 49960 | 2021-03-10 | 2021-03-23 | 100% | 49960 |  | TeaM- Sual (DOE) |  | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+100