## TFU 4th qtr 2024
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: I |  |  | CALENDAR YEAR: | 2024
PROVINCE: PANGASINAN |  |  | QUARTER: | 4
CITY/MUNICIPALITY: ASINGAN
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Construction of a Multi-Purpose Building at Poblacion West, Asingan, Pangasinan, funded under the Local Government Support Fund – Financial Assistance to Local Government Units (LGSF-FA to LGUs) and Support for Capital Outlays and Social Programs, Fiscal Year 2023, General Appropriations Act (GAA), Republic Act No. 11936 |  | Public Market, Asingan, Pangasinan | 49999331.49 | 2024-06-24 | 2025-01-29 | 54.28% | 27141704.7 |  | LGSF - FA ₱50M | -22857626.79 | 22857626.79 | 2024-08-02 | 2025-01-29
Construction of Asingan Children's Park at the Public Plaza, Poblacion East, Asingan, Pangasinan |  | Public Plaza, Asingan, Pangasinan | 3240000 | 2024-06-14 | 2024-12-03 | 100% | 1446808.27 |  | Funds from DILG P1,800,000 (SGLG Incentive Fund) + LGU Counterpart P1,440,000 |  | 1793191.73
Construction of Farm to Market Road in Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 26995756.09 | 2024-11-13 | 2025-08-04 | 49.21% | 13283607.9 |  | Funds from DAR |  | 13712148.19
National Nutrition Council for the Travelling Allowance of Barangay Nutrition Scholars (BNS) for the period of January to December 2024 Dated 12/11/2024 LBP# 228327 OR#2111611 |  | Asingan, Pangasinan | 25600 | 2024-12-01 | 2024-12-31 | 100% | 25600 |  | Funds from Province |  | 0
Funds from DAR for the construction of 6 various Farm to Market Road, Asingan Pangasinan CM:12/19/2024 |  | Asingan, Pangasinan | 29475000 | [5 empty] | for bidding - Funds from DAR - 6 various FMR 30M (1.75% Monitoring Fee) |  | 98.25
Funds from DILG-Regional Office 1 for the payment of SGLG Incentive Fund 2024 Dated 12/23/2024 LBP#1847800 OR#2111625 |  | Asingan, Pangasinan | 1153000 | [5 empty] | for bidding - Funds from DILG -SGLG Incentive Fund 2024 |  | 1153000
Funds from Philippine Sports Commission (PSC) for Sponsorship Assistance for the conduct of their Sports Development Activities per BR No. 879-2024 Dated 12/9/2024 LBP#552290 OR#2111604 |  | Asingan, Pangasinan | 300000 | [5 empty] | for bidding - funds from Philippine Sports Commission |  | 300000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+264

## TFU 3rd qtr 2024
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3rd QUARTER, CY 2024
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Wages of 998 TUPAD Beneficiaries from DOLE RO1 dated 05/01/2024, LBP No. 1847402, OR No. 0915564 |  | Asingan, Pangasinan | 4341300 | 2024-05-09 | 2024-09-30 | 100% | 4341300 |  | Funds from DOLE | 0
Construction of a Multi-Purpose Building at Poblacion West, Asingan, Pangasinan, funded under the Local Government Support Fund – Financial Assistance to Local Government Units (LGSF-FA to LGUs) and Support for Capital Outlays and Social Programs, Fiscal Year 2023, General Appropriations Act (GAA), Republic Act No. 11936 |  | Public Market, Asingan, Pangasinan | 49999331.49 | 2024-06-24 | 2024-08-13 | 15% | 7499899.72 |  | LGSF - FA ₱50M | -42499431.77
Construction of Asingan Children's Park at the Public Plaza, Poblacion East, Asingan, Pangasinan |  | Public Plaza, Asingan, Pangasinan | 3240000 | 2024-06-14 | 2024-09-12 | 44.65% | 1446808.27 |  | Funds from DILG P1,800,000 (SGLG Incentive Fund) + LGU Counterpart P1,440,000
To recognize deposit from DOH CHD 1 for the payment of Health Emergency Allowance (HEA) for the month of April to May 2023 Dated 7/29/2024 LBP#0002425166 OR#0920348 |  | Asingan, Pangasinan | 489437.5 | 2024-08-19 | 2024-08-28 | 100% | 489437.5 |  | Funds from DOH RO1
Health Emergency Allowance (HEA) for the Public and Private Health Worker for the period of July to December 2021, July to September 2022, October -December 2022 and January- March 2023 |  | Asingan, Pangasinan | 5126375 | 2024-08-05 | 2024-08-22 | 100% | 5126375 |  | Funds from DOH RO1 (Refunded P185,250 to DOH RO1 last 8/22/2024 JEV#300-24-08-0231)
Funds received from DAR for Local Government Support Fund - Financial Assistance for the construction of Farm to Market Road in Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 27000000 | [5 empty] | to be bid
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+90

## TFU 2nd qtr 2024
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER, CY 2024
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Health Emergency Allowance (HEA) for Public and Private Health Workers (HCWs) and Non-HCWs for the months of March to June 2022, dated 03/11/2024, LBP No. 1824884 |  | Asingan, Pangasinan | 1521375 | 2024-04-24 | 2024-04-30 | 100% | 1521375 |  | Funds from DOH | 0
Wages of 998 TUPAD Beneficiaries from DOLE RO1 dated 05/01/2024, LBP No. 1847402, OR No. 0915564 |  | Asingan, Pangasinan | 4341300 | 2024-05-09 | 2024-08-31 | 99.7% | 4328250 |  | Funds from DOLE | -13050
Construction of a Multi-Purpose Building at Poblacion West, Asingan, Pangasinan, funded under the Local Government Support Fund – Financial Assistance to Local Government Units (LGSF-FA to LGUs) and Support for Capital Outlays and Social Programs, Fiscal Year 2023, General Appropriations Act (GAA), Republic Act No. 11936 |  | Public Market, Asingan, Pangasinan | 49999331.49 |  |  | 0% | 0 |  | LGSF - FA ₱50M (bid, but not yet awarded) | -49999331.49
Construction of Asingan Children's Park at the Public Plaza, Poblacion East, Asingan, Pangasinan |  | Public Plaza, Asingan, Pangasinan | 3240000 | 2024-06-14 | 2024-09-12 | 45% | 0 |  | Funds from DILG P1,800,000 (SGLG Incentive Fund) + LGU Counterpart P1,440,000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+90

## TFU 1st qtr 2024
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2024
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
To recognize cash deposit of the TUPAD wages for 973 TUPAD Workers for the Implementation of TUPAD in Asingan, Pangasinan with LBP#0001840250 Dated 12/21/2024 (OR#0756272) |  | Asingan, Pangasinan | 3997000 | 2023-12-29 | 2024-02-28 | 100% | 3997000 |  | Liquidated 3/27/2024 | 0
Barangay Newly Elected Officials Training and Seminar (BNEO) Basic Orientation Course held on March 11-14, 2024 |  | Asingan, Pangasinan | 299820.62 | 2024-03-11 | 2024-03-14 | 100% | 299820.62 |  | BNEO | 0
Transfer of RPT and CTC Barangay Shares to Various Accounts of Barangay in Asingan, Pangasinan |  | Asingan, Pangasinan | 918025.9 | 2024-03-01 | 2024-03-04 | 100% | 918025.9 |  | RPT & CTC 4th Qtr 2023 | 0
Philhealth MCP and TBDOTS Accreditation Fee for CY 2024 of RHU I & II and renewal of Accreditation for the Primary Care Physician |  | Asingan, Pangasinan | 12700 | 2024-02-07 | 2024-02-07 | 100% | 12700 |  | HCI Charges & PHIC Capitation
Medicines for the treatment of Pulmonary Tuberculosis |  | Asingan, Pangasinan | 99110 | 2024-02-13 | 2024-02-13 | 100% | 99110 |  | HCI Charges
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor