## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2024
PROVINCE: | PANGASINAN |  | QUARTER: | 1
CITY/MUNICIPALITY: | ASINGAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Repair of Slaughterhouse, Asingan, Pangasinan NTP: 12/05/2023 SWA: 12/15/2023 70.12% CP: 599,819.88 | Asingan, Pangasinan | 599819.88 | 2023-12-05 | 2024-01-04 | 100% | 599819.88 |  | cost incurred to date
Construction of Multi-purpose Hall (Food court old DA building area) Asingan, Pangasinan NTP: 12/05/2023 SWA: 12/12/2023 25.02% CP: 1,999,892.37 | Asingan, Pangasinan | 1999892.37 | 2023-12-05 | 2024-02-21 | 100% | 1999892.37 |  | cost incurred to date
Procurement of Patrol Vehicles for use at Brgy. Baro and Sanchez, Asingan, Pangasinan NTP: 02/09/2024 Delivery Date: 02/29/2024 CP: 2,160,000.00 | Baro, Asingan, Pangasinan | 2160000 | 2024-02-09 | 2024-02-29 | 100% | 2160000
Backfilling of 20 truck loads of mixed sand at some parts of Farm to Market Road, Barangay Carosucan Sur, Asingan, Pang. NTP: 12/12/2023 SWA: 12/14/2023 100% CP: 196,351.51 | Carosucan Sur, Asingan, Pangasinan | 196351.51 | 2023-12-12 | 2023-12-14 | 100% | 19400
Installation of Street Lights at Zone 1, San Vicente East, Asingan, Pangasinan NTP: 02/09/2024 SWA: 02/22/2024 100% CP: 299,778.43 | San Vicente East, Asingan, Pangasinan | 299778.43 | 2024-02-09 | 2024-02-22 | 100% | 299778.43
Purchase of New Engine Hammer Mill at MRF, Asingan, Pangasinan NTP: 02/08/2024 Delivery Date: 02/18/2024 CP: 149,000.00 | Asingan, Pangasinan | 149000 | 2024-02-08 | 2024-02-18 | 100% | 149000
Construction of Perimeter Fence at STAC Building, Macalong, Asingan, Pangasinan NTP: 02/09/2024 SWA: 03/06/2024 100% CP: 499,834.06 | Macalong, Asingan, Pangasinan | 499834.06 | 2024-02-09 | 2024-03-06 | 100% | 499834.06
Construction of CHB Lined Canal at Zone 3 Carosucan Norte, Asingan, Pangasinan NTP: 02/09/2024 SWA: 03/06/2024 100% CP: 499,864.55 | Carosucan Norte, Asingan, Pangasinan | 499864.55 | 2024-02-09 | 2024-03-06 | 100% | 499864.55
Reimbursement of Solid Waste Tipping Fee from January 18 to February 28, 2024 CP: 21,811.00 | Asingan, Pangasinan | 21811 | 2024-01-18 | 2024-02-28 | 100% | 21811
Installation of On-Grid/Hybrid Solar Power Source for Municipal Buildings, Asingan, Pangasinan NTP: 02/09/2024 SWA: 03/22/2024 71.49% CP: 5,967,357.48 | Asingan, Pangasinan | 5967357.48 | 2024-02-09 | 2024-03-22 | 71.49% | 4266061.38
Installation of Wall Ceiling of Multi-Purpose Hall of Barangay Ariston East, Asingan, Pangasinan NTP: 12/28/2023 SWA: 12/29/2023 100% CP: 98,608.65 | Ariston East, Asingan, Pangasinan | 98608.65 | 2023-12-28 | 2023-12-29 | 100% | 98608.65
Rehabilitation of drainage canal at Zone 3, Barangay Baro, Asingan, Pangasinan NTP: 12/11/2023 SWA: 12/18/2023 100% CP: 99,995.75 | Baro, Asingan, Pangasinan | 99995.75 | 2023-12-11 | 2023-12-18 | 100% | 99995.75
Economic Development (pls list down specific projects)
Environmental Management (pls list down specific projects)
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| EMELY S. BADUA |  |  |  | ENGR. CARLOS F. LOPEZ, JR.
| Municipal Budget Officer |  |  |  | Municipal Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43