## 2ND Qtr 20% LDF
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2024
PROVINCE: | PANGASINAN |  | QUARTER: | 2
CITY/MUNICIPALITY: | ASINGAN
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date | Remarks
SOCIAL DEVELOPMENT
Installation of On-Grid/Hybrid Solar Power Source for Municipal Buildings, Asingan, Pangasinan NTP: 02/09/2024 SWA: 4/8/2024 100% CP: 5,967,357.48 |  | Asingan, Pangasinan | 5967357.48 | 2024-02-09 | 60 | 2024-04-09 | 100% | 5967357.48 | paid in the 1st qtr of 2024 - P4,266,061.38 |  |  | 0
To payment for the Construction of Multi-Purpose Hall at Brgy Bobonan, Asingan, Pangasinan. SWA: 04/15/2024-100% NTP: 02/09/2024-30 days CP: 499,808.80 |  | Bobonan, Asingan, Pangasinan | 499808.8 | 2024-02-09 | 66 | 2024-04-15 | 100% | 499808.8 |  |  |  | 0
Reimbursement of Solid Waste Tipping Fee from March 1, 2024 to April 11, 2024 |  | Asingan, Pangasinan | 20179 | 2024-03-01 | 42 | 2024-04-12 | 100% | 20179 |  |  |  | 0
To payment for the fabrication and installation of window grills at Brgy. Dupac Child Development Center and Health Center, Asingan, Pangasinan NTP: 03/07/2024 SWA: 03/20/2024 100% CP: 165,210.00 |  | Dupac, Asingan, Pangasinan | 165210 | 2024-03-07 | 14 | 2024-03-21 | 100% | 165210 |  |  |  | 0
To payment for the construction of reinforced concrete pipe culvert at Ciriaco Altura Road at Brgy. Domanpot, Asingan, Pangasinan NTP: 03/11/2024 SWA: 03/18/2024 CP: 199,880.00 RI: 0113050130015 |  | Domanpot, Asingan, Pangasinan | 199880 | 2024-03-11 | 8 | 2024-03-19 | 100% | 199880 |  |  |  | 0
To payment for the construction of Multi-Purpose Concrete Pavement at Brgy. Domanpot, Asingan, Pangasinan NTP: 03/11/2024 SWA: 03/18/2024 CP: 199,560.00 |  | Domanpot, Asingan, Pangasinan | 199560 | 2024-03-11 | 8 | 2024-03-19 | 100% | 199560 |  |  |  | 0
Reimbursement of Solid Waste Tipping Fee from April 12 to May 15, 2024 |  | Asingan, Pangasinan | 21267 | 2024-04-12 | 43 | 2024-05-25 | 100% | 21267 |  |  |  | 0
To payment for the contract for the procurement of Garbage Truck for the Municipality of Asingan, Pangasinan NTP: 04/29/2024 SWA: 05/08/2024 CP: 1,990,000.00 |  | Asingan, Pangasinan | 1990000 | 2024-04-29 | 10 | 2024-05-09 | 100% | 1990000 |  |  |  | 0
Installation of Solar Street Lights at Sitio Aragaag, Bantog, Asingan, Pangasinan NTP: 04/29/2024 SWA: 06/04/2024 100% CP: 1,499,885.13 |  | Bantog, Asingan, Pangasinan | 1499885.13 | 2024-04-29 | 45 | 2024-06-13 | 100% | 1499885.13 |  |  |  | 0
To payment for the Continuation of the Concreting of FMR at Baro-Dumaquit, Domanpot, Asingan, Pangasinan NTP:04/29/24 SWA: 5/10/24 100% CP: 499,773.89 RID0113050130007 |  | Baro-Domanpot, Asingan, Pangasinan | 299773.89 | 2024-04-29 | 12 | 2024-05-11 | 100% | 299773.89 |  |  |  | 0
To payment of his contract for the installation of Solar Street Lights at Brgy. Coldit, Asingan, Pangasinan NTP: 04/29/2024 SWA: 05/09/2024 100% CP: 299,880.30 |  | Coldit, Asingan, Pangasinan | 299880.3 | 2024-04-29 | 11 | 2024-05-10 | 100% | 299880.3 |  |  |  | 0
To payment of his contract for the continuation of the concreting of Don Luis Butao FMR at Domanpot, Asingan, Pangasinan NTP: 04/29/2024 SWA: 05/22/2024 100% CP: 499,773.89 RI: 0113050130013 |  | Domanpot, Asingan, Pangasinan | 499773.89 | 2024-04-29 | 24 | 2024-05-23 | 100% | 499773.89 |  |  |  | 0
To payment of his contract for the procurement of Patrol Vehicle for use at Brgy. Dupac, Asingan, Pangasinan NTP: 04/29/2024 SWA: 05/14/2024 CP: 1,080,000.00 |  | Dupac, Asingan, Pangasinan | 800000 | 2024-04-29 | 16 | 2024-05-15 | 100% | 800000 |  |  |  | 0
To payment of his contract for the Concreting of Farm to Market Road at Zone 4 Macalong, Asingan, Pangasinan NTP: 04/29/2024 SWA: 05/10/2024 100% CP: 299,377.80 |  | Macalong, Asingan, Pangasinan | 299377.8 | 2024-04-29 | 12 | 2024-05-11 | 100% | 299377.8 |  |  |  | 0
To payment for the contract for the procurement of Dump Truck for use at Brgy. Palaris, Asingan, Pangasinan NTP: 04/29/2024 SWA: 05/08/2024 CP: 1,595,000.00 |  | Palaris, Asingan, Pangasinan | 1595000 | 2024-04-29 | 10 | 2024-05-09 | 100% | 1595000 |  |  |  | 0
To payment for the installation of Solar Streetlights at Zone 5, Brgy. Cabalitian, Asingan, Pangasinan NTP: 05/07/2024 SWA: 05/15/2024 100% CP: 99,994.27 |  | Cabalitian, Asingan, Pangasinan | 99994.27 | 2024-05-07 | 9 | 2024-05-16 | 100% | 99994.27 |  |  | 0 | 0
To payment of his contract for the concreting of Farm to Market Road at Sitio Turod, Brgy. Ariston West, Asingan, Pangasinan NTP: 05/17/2024 SWA: 06/13/2024 100% CP: 499,877.34 RI: 0113050040013 |  | Ariston West, Asingan, Pangasinan | 499877.34 | 2024-05-17 | 27 | 2024-06-13 | 100% | 499877.34 |  |  |  | 0
To payment for his contract for the construction of Farm to Market Road Zone 4, San Vicente West, Asingan, Pangasinan NTP: SWA: 06/04/2024 100% CP: 299,874.15 RI: 0113050190007 |  | San Vicente West, Asingan, Pangasinan | 299874.15 | 2024-05-17 | 19 | 2024-06-05 | 100% | 299874.15 |  |  | 0 | 0
To payment of his contract for the concreting of Barangay Road at Sitio Hacienda at Toboy, Asingan, Pangasinan NTP: 05/17/2024 SWA: 06/14/2024 100% CP: 299,879.01 RI: 0113050210003 |  | Toboy, Asingan, Pangasinan | 299879.01 | 2024-05-17 | 29 | 2024-06-15 | 100% | 299879.01 |  |  | 0 | 0
To payment of Filling Materials River Mixed Sand & Gravel for the Backfilling of New Consejo De Bente Nueve FMR - Brgy. Car. Sur, Asingan, Pangasinan PO: 05/22/2024 SWA: 05/24/2024 100% CP:99,397.50 |  | Carosucan Sur, Asingan, Pangasinan | 99397.5 | 2024-05-22 | 3 | 2024-05-25 | 100% | 99397.5 |  |  |  | 0
To payment for the installation of four (4) units solar streetlights at Zone 5, Brgy. Cabalitian, Asingan, Pangasinan NTP: 06/03/2024 SWA: 06/10/2024 100% CP: 97,768.27 |  | Cabalitian, Asingan, Pangasinan | 97768.27 | 2024-06-03 | 8 | 2024-06-11 | 100% | 97768.27 |  |  | 0 | 0
[10 empty] | 0 | 0 | 0
Economic Development (pls list down specific projects)
Environmental Management (pls list down specific projects)
[10 empty] | 0 | 0 | 0
Total 20% LDF for the 2nd Qtr 2024 (net of 1st qtr payment) | [7 empty] | 11487682.45 |  | -11487682.45
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
EMELY S. BADUA | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Budget Officer | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+[Contract Duration]